## Summary
Company Initiative | OOTB ACA
Epic, Story, Bug | 423 | Closed | 353
Progress Bar
Business Initiative | OOTB ACA

## Generated Cards
Key | PRODDEL-796 | Release Vehicle
Epic, Story, Bug | 20 | Closed | 0
Progress Bar
Theme | VB: OOTB Production Readiness & Trials
Summary
Key | PRODDEL-778 | Release Vehicle
Epic, Story, Bug | 36 | Closed | 8
Progress Bar
Theme | ACA 1.7 (EA Feedback)
Summary
Key | PRODDEL-777 | Release Vehicle
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | ACA 1.6 (TBD)
Summary
Key | PRODDEL-776 | Release Vehicle | 2018-09-06
Epic, Story, Bug | 46 | Closed | 46
Progress Bar
Theme | Feedback - UX improvements
Summary
Key | PRODDEL-775 | Release Vehicle
Epic, Story, Bug | 27 | Closed | 5
Progress Bar
Theme | Library Management
Summary
Key | PRODDEL-774 | Release Vehicle
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | Extensibility Phase 2
Summary
Key | PRODDEL-773 | Release Vehicle | 2018-09-06
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | Commenting Enhancements
Summary
Key | PRODDEL-772 | Release Vehicle | 2018-09-06
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | Integrate Existing ADF Components
Summary
Key | PRODDEL-731 | Release Vehicle | 2018-09-06
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | Extensibility Phase 1
Summary | [All Issues¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20ACA%20AND%20fixVersion%20%3D%20"ACA%201.4"%20AND%20"Epic%20Link"%20%3D%20ACA-1507]
Key | PRODDEL-569 | Release Vehicle
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | Quick Share
Summary | *Story:* As a user I want to be able to share files quickly and easily with any user regardless of whether they have access to the file so that they can view and download. *Value:* * Provide customers, partners and community with quick file sharing capabilities, that are required in order to collaborate with users external to the ACS platform. * Enable the deprecation of my.alfesco.com by
Key | PRODDEL-541 | Release Vehicle
Epic, Story, Bug | 0 | Closed | 0
Progress Bar
Theme | VB: Alfresco ADF Content App DBP SSO
Summary | *Story:* As an IT Administrator I want my users to authenticate with the content application through the organizations chosen single sign on provider. *Value:* Integration of Alfresco DBP SSO with the ADF Content Application. *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: ADF Team, Developer Community, Platform Services Team ** (/) Sponsors are: [~ohejls
Key | PRODDEL-540 | Release Vehicle | 2018-07-04
Epic, Story, Bug | 52 | Closed | 52
Progress Bar
Theme | Faceted Search
Summary | *Story:* As a developer I want my ADF application to have a filtered search experience so that users can easily reduce search results and quickly find the right file. *Value:* * Creation of faceted search components that enable developers to create an easy to use search UI * Integration of the search components into the example application which demonstrates Alfresco Search Services (SOLR)
Key | PRODDEL-539 | Release Vehicle | 2018-04-20
Epic, Story, Bug | 32 | Closed | 32
Progress Bar
Theme | VB: Metadata & Versioning
Summary | *Story:* As a developer I want my ADF application to show metadata information for files so that users can view and update attributes relating to files. As a developer I want my ADF application to provide for files so that users can upload new versions and download or revert to previous versions of a file. *Value:* Integration of Content Services ADF components that are available in the A
Key | PRODDEL-529 | Release Vehicle | 2018-03-12
Epic, Story, Bug | 24 | Closed | 24
Progress Bar
Theme | VB: Enhanced File Viewer
Summary | *Story:* As a developer I want my ADF application to have a viewer that displays any type of file natively in my users browser so that they can easily view content without having to download and open in specific applications. *Value:* * A file viewer that leverages the ACS platform capabilities for creating renditions from many various file types for display in a web browser * Documents, Ima
Key | PRODDEL-355 | Release Vehicle | 2017-12-15
Epic, Story, Bug | 186 | Closed | 186
Progress Bar
Theme | VB: Alfresco example Content App (v1.0)
Summary | *Story:* As a developer/SE, I can access the source code of an example application for Alfresco Content Services built using the Alfresco ADF so that I can: * easily demonstrate the basic file management capabilities using the ADF * understand application development patterns when using the ADF * quickly build a tailored ACS demo *Value:* * Alfresco Account Manager: ACS+ADF demos at

## BurnUpData
Date | Remaining | Total |  | Trend | Closed
2018-05-21 12:00 |  |  |  |  | 0
2018-05-28 12:00 |  |  |  |  | 0
2018-06-04 12:00 |  |  |  |  | 0
2018-06-11 12:00 |  |  |  |  | 0
2018-06-18 12:00 |  |  |  |  | 0
2018-06-25 12:00 |  |  |  |  | 0
2018-07-02 12:00 |  |  |  |  | 0 | 0
2018-07-09 12:00 |  |  | Jira update |  | 0 | 31
2018-07-16 12:00 | 0 | 0 | 591 |  | 0 | 11
2018-07-23 12:00 | 69 | 369 | 300 | 69 | 69 | 11
2018-07-30 12:00 | 62 | 373 | 311 | 62 | -7 | 11
2018-08-06 12:00 | 62 | 376 | 314 | 62 | 0 | 4
2018-08-13 12:00 | 61 | 379 | 318 | 61 | -1 | 1
2018-08-20 12:00 | 61 | 381 | 320 | 61 | 0 | 9
2018-08-27 12:00 | 55 | 382 | 327 | 55 | -6 | 144
2018-09-03 12:00 | 60 | 389 | 329 | 60 | 5
2018-09-10 12:00 | 64 | 412 |  | 64 | 4
2018-09-17 12:00 | 60 | 411 |  | 60 | -4
2018-09-24 12:00 | 70 | 423 |  | 70 | 10
2018-10-01 12:00 |  |  |  | 73 | FALSE
2018-10-08 12:00 |  |  |  | 76 | FALSE
2018-10-15 12:00 |  |  |  | 79 | FALSE
2018-10-22 12:00 |  |  |  | 82 | FALSE
2018-10-29 12:00 |  |  |  | 85 | FALSE
2018-11-05 12:00 |  |  |  | 88 | FALSE
2018-11-12 12:00 |  |  |  | 91 | FALSE
2018-11-19 12:00 |  |  |  | 94 | FALSE
2018-11-26 12:00 |  |  |  | 97 | FALSE
2018-12-03 12:00 |  |  |  | 100 | FALSE
2018-12-10 12:00 |  |  |  | 103 | FALSE
2018-12-17 12:00 |  |  |  | 106 | FALSE
2018-12-24 12:00 |  |  |  | 109 | FALSE
2018-12-31 12:00 |  |  |  | 112 | FALSE
Formulas:
Date = [Date, row above]+7

## Backlog (hidden)
Key | Summary | Description | Status | Labels | Fix Version/s
PRODDEL-796 | VB: OOTB Production Readiness & Trials |  | New | OOTBNov2018 | ACA 1.6,ACA 1.7
PRODDEL-778 | ACA 1.7 (EA Feedback) |  | New | OOTBNov2018 | ACA 1.7
PRODDEL-777 | ACA 1.6 (TBD) |  | New | OOTBNov2018 | ACA 1.6
PRODDEL-776 | Feedback - UX improvements |  | Closed | OOTBNov2018 | ACA 1.4
PRODDEL-775 | Library Management |  | Open | OOTBNov2018 | ACA 1.5
PRODDEL-774 | Extensibility Phase 2 |  | In Progress | OOTBNov2018 | ACA 1.5
PRODDEL-773 | Commenting Enhancements |  | Closed | OOTBNov2018 | ACA 1.4
PRODDEL-772 | Integrate Existing ADF Components |  | Closed | OOTBNov2018 | ACA 1.4
PRODDEL-731 | Extensibility Phase 1 | [All Issues¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20ACA%20AND%20fixVersion%20%3D%20"ACA%201.4"%20AND%20"Epic%20Link"%20%3D%20ACA-1507] | Closed | OOTBNov2018 | ACA 1.4
PRODDEL-569 | Quick Share | *Story:* As a user I want to be able to share files quickly and easily with any user regardless of whether they have access to the file so that they can view and download. *Value:* * Provide customers, partners and community with quick file sharing capabilities, that are required in order to collaborate with users external to the ACS platform. * Enable the deprecation of my.alfesco.com by facilitating the external sharing of content to prospective customers by Alfresco field and sales organisations. * Provide prospective customers with an incredible product experience during engagement with Alfresco *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: Sales, Community ** (/) Sponsors are: [~jknowles], [~mhowarth], [~ohejlskov], [~dvuika] * Product Requirements: ** (/) Story and value have been described in this issue ** (/) Link to user stories (JIRA epics, stories, etc) has been provided ** (x) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria have been specified ** (i) Security criteria have been specified ** (x) Test plan is in place (team or PRR) ** (x) UX, UA, I18N and L10N requirements are understood ** (i) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments) * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (/) Architect: [~dvuika] *** (i) PRR: NA *** (x) UA: TBC *** (x) UX: TBC *** (/) I18N and L10N ** (/) Value Bundle dependencies have been linked using a 'depends on' association * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | In Progress | OOTBNov2018 | ACA 1.5
PRODDEL-541 | VB: Alfresco ADF Content App DBP SSO | *Story:* As an IT Administrator I want my users to authenticate with the content application through the organizations chosen single sign on provider. *Value:* Integration of Alfresco DBP SSO with the ADF Content Application. *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: ADF Team, Developer Community, Platform Services Team ** (/) Sponsors are: [~ohejlskov], [~jknowles], [~resplin] * Product Requirements: ** (/) Story and value have been described in this issue ** (x) Link to user stories (JIRA epics, stories, etc) has been provided ** (x) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria have been specified: NA ** (i) Security criteria have been specified: NA ** (/) Test plan is in place (team or PRR): Covered by ACA testers ** (/) UX, UA, I18N and L10N requirements are understood ** (i) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments): NA * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (/) Architect: [~dvuika] *** (i) PRR: NA *** (i) UA: tbd *** (/) UX: tbb *** (/) I18N and L10N ** (/) Value Bundle dependencies have been linked using a 'depends on' association * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | New | OOTBNov2018 | ACA 1.7
PRODDEL-540 | Faceted Search | *Story:* As a developer I want my ADF application to have a filtered search experience so that users can easily reduce search results and quickly find the right file. *Value:* * Creation of faceted search components that enable developers to create an easy to use search UI * Integration of the search components into the example application which demonstrates Alfresco Search Services (SOLR) built using the ADF. *Issues:* * [All issues¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20%22Alfresco%20Example%20Content%20App%22%20and%20(issueFunction%20in%20aggregateExpression(%22Story%20Points%22%2C%20%22StoryPoints.sum()%22)%20and%20fixVersion%20%3D%201.3)] *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: ADF Team, Developer Community, Alfresco SEs ** (/) Sponsors are: [~ohejlskov], [~jknowles], [~hpeek] * Product Requirements: ** (/) Story and value have been described in this issue ** (/) Link to user stories (JIRA epics, stories, etc) has been provided ** (/) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria have been specified: NA ** (i) Security criteria have been specified: NA ** (/) Test plan is in place (team or PRR): Covered by ACA testers ** (/) UX, UA, I18N and L10N requirements are understood ** (i) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments): NA * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (/) Architect: [~dvuika] *** (i) PRR: NA *** (i) UA: done previously by Andy *** (/) UX: designs provided already *** (/) I18N and L10N ** (/) Value Bundle dependencies have been linked using a 'depends on' association * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | Closed | OOTBNov2018 | ACA 1.3
PRODDEL-539 | VB: Metadata & Versioning | *Story:* As a developer I want my ADF application to show metadata information for files so that users can view and update attributes relating to files. As a developer I want my ADF application to provide for files so that users can upload new versions and download or revert to previous versions of a file. *Value:* Integration of Content Services ADF components that are available in the ADF into the example content app: * demonstration of core content capabilities in the ADF example app * Feedback and improvement iterations on ACS components * Fundamental content management features that sales can use in prospective customer demos *Issues:* * [All issues¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20%22Alfresco%20Example%20Content%20App%22%20and%20(issueFunction%20in%20aggregateExpression(%22Story%20Points%22%2C%20%22StoryPoints.sum()%22)%20and%20fixVersion%20%3D%201.2)] *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: ADF Team, Developer Community ** (/) Sponsors are: [~ohejlskov], [~jknowles] * Product Requirements: ** (/) Story and value have been described in this issue ** (/) Link to user stories (JIRA epics, stories, etc) has been provided ** (/) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria have been specified: NA ** (i) Security criteria have been specified: NA ** (/) Test plan is in place (team or PRR): Covered by ACA testers ** (/) UX, UA, I18N and L10N requirements are understood ** (i) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments): NA * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (/) Architect: [~dvuika] *** (i) PRR: NA *** (i) UA: done previously by Andy *** (/) UX: designs provided already *** (/) I18N and L10N ** (/) Value Bundle dependencies have been linked using a 'depends on' association * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | Closed | ACA,OOTBNov2018 | ACA 1.2
PRODDEL-529 | VB: Enhanced File Viewer | *Story:* As a developer I want my ADF application to have a viewer that displays any type of file natively in my users browser so that they can easily view content without having to download and open in specific applications. *Value:* * A file viewer that leverages the ACS platform capabilities for creating renditions from many various file types for display in a web browser * Documents, Images, Audio, Video *Issues:* * [All issues¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20%22Alfresco%20Example%20Content%20App%22%20and%20issueFunction%20in%20aggregateExpression(%22Story%20Points%22%2C%20%22StoryPoints.sum()%22)%20and%20fixVersion%20%3D%201.1] *Checklist: (x), (/), (!) or (i)* * Stakeholders: ** (/) Stakeholders are: ADF Team, Developer Community ** (/) Sponsors are: [~ohejlskov], [~jknowles] * Product Requirements: ** (/) Story and value have been described in this issue ** (/) Link to user stories (JIRA epics, stories, etc) has been provided ** (/) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria have been specified: NA ** (i) Security criteria have been specified: NA ** (/) Test plan is in place (team or PRR): Covered by ADF testers ** (/) UX, UA, I18N and L10N requirements are understood ** (i) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments): NA * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (/) Architect: [~dvuika] *** (i) PRR: NA *** (i) UA: done previously by Andy *** (/) UX: designs provided already *** (/) I18N and L10N ** (/) Value Bundle dependencies have been linked using a 'depends on' association * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | Closed | ACA,OOTBNov2018 | ACA 1.1
PRODDEL-355 | VB: Alfresco example Content App (v1.0) | *Story:* As a developer/SE, I can access the source code of an example application for Alfresco Content Services built using the Alfresco ADF so that I can: * easily demonstrate the basic file management capabilities using the ADF * understand application development patterns when using the ADF * quickly build a tailored ACS demo *Value:* * Alfresco Account Manager: ACS+ADF demos at early sales cycle stage without customisation * Alfresco Solutions Engineer: create tailored/custom demos later in the sales cycle using the example app as a base * External developer: code reference/guide that shows me how to create a whole application from the ADF components * External developer: starting point for creating a Content application *Issues:* * [All issues: ACA version 1.0¦https://issues.alfresco.com/jira/issues/?jql=project%20%3D%20%22Alfresco%20Example%20Content%20App%22%20%20and%20issueFunction%20in%20aggregateExpression(%22Story%20Points%22%2C%20%22StoryPoints.sum()%22)%20and%20fixVersion%20%3D%201.0] *Checklist: (x), (/) or (i)* * Stakeholders: ** (/) Stakeholders are: [~jknowles], [~ohejlskov], [~mromano], [~dgruber], [~rallegre] ** (/) Sponsors are: [~ckitchener], [~tdemeo], [~cwiborg] * Product Requirements: ** (/) Story and value have been described in this issue ** (/) Link to user stories (JIRA epics, stories, etc) has been provided ** (/) Value bundle has been guess-sized in this issue * Non-functional requirements: ** (i) Performance and Scalability criteria are not applicable since this is an example application with no compiled binary for production ** (i) Security criteria are deemed not applicable at this time, the onus for security is on the developer compiling and productising their own app ** (/) Test plan is in place (team) ** (/) UX, UA, I18N and L10N requirements are understood: *** (/) App built following XD's Material Design Standards *** (/) App UI text and messages fully reviewed by Andy Healey *** (/) Localisation completed ** (x) There are stories in this or other value bundles to capture updates to release vehicles (installers, quick starts, reference deployments) * Dependencies: ** (/) Scrum team has been identified (Dev, PO, SM) ** Extended scrum team are ready: *** (x) Architect *** (x) PRR *** (/) UA - Andy Healey *** (/) UX - Stephen Sarpong *** (/) I18N and L10N - Gloria Broadbent ** (i) Value Bundle dependencies on [ADF 2.0¦https://issues.alfresco.com/jira/issues/?jql=project+%3D+PRODDEL+AND+fixVersion+%3D+%22ADF+2.0%22] & [ACS 5.2.2¦https://issues.alfresco.com/jira/issues/?jql=project+%3D+PRODDEL+AND+fixVersion+%3D+%22ACS+5.2.2%22] * Programme Management: ** (x) Release milestones have been agreed; ** (x) Release simulations have been agreed, where necessary | Closed | OOTBNov2018 | ACA 1.0

## SetUp (hidden)
Company Initiative | OOTB ACA
Business Initiative | OOTB ACA
Label | OOTBNov2018
Start Date | 2018-03-01

## Database
Summary VB Counts: | 15 | 0
Summary VB Counts: | 15 | 0
PRODDEL-796 | 20 | 0
PRODDEL-778 | 36 | 8
PRODDEL-777 | 0 | 0
PRODDEL-776 | 46 | 46 | 2018-09-06
PRODDEL-775 | 27 | 5
PRODDEL-774 | 0 | 0
PRODDEL-773 | 0 | 0 | 2018-09-06
PRODDEL-772 | 0 | 0 | 2018-09-06
PRODDEL-731 | 0 | 0 | 2018-09-06
PRODDEL-569 | 0 | 0
PRODDEL-541 | 0 | 0
PRODDEL-540 | 52 | 52 | 2018-07-04
PRODDEL-539 | 32 | 32 | 2018-04-20
PRODDEL-529 | 24 | 24 | 2018-03-12
PRODDEL-355 | 186 | 186 | 2017-12-15
Totals | 423 | 353

## Card Template (hidden)
Key |  | Release Vehicle
Epic, Story, Bug | 5 | Closed | 2
Progress Bar
Theme
Summary
Company Initiative
Epic, Story, Bug | 5 | Closed | 5
Progress Bar
Business Initiative

## Copy of BurnUpData (hidden)
Date | Remaining
2018-05-21 | 100
2018-05-28 | 95
2018-06-04 | 90
2018-06-11 | 85
2018-06-18 | 80
2018-06-25 | 75
2018-07-02 | 80
2018-07-09 | 75
2018-07-16 | 70
2018-07-23 | 90
2018-07-30 | 85
2018-08-06 | 80
2018-08-13 | 50
2018-08-20 | 45
2018-08-27 | 40
2018-09-03 | 20
2018-09-10 | 15
2018-09-17 | 15
2018-09-24 | 10
2018-10-01 | 2
#REF!

## Copy of Backlog (hidden)
Key | Summary
PRODDEL-664 | Migration tool selection
PRODDEL-654 | VB: ACS Changes for AWS Migration
PRODDEL-653 | VB: ACS uses AWS Services
PRODDEL-648 | VB: Scalable Rules and Metadata Extraction
PRODDEL-611 | VB: ACS Load Tests on AWS
PRODDEL-221 | VB: Scalable Transformations
PRODDEL-220 | VB: ACS Audit Data on AWS